## Executive Dashboard
Metric | Value
Total sample records | 12
Ready for sample review | 6
Needs review | 6
Overdue not approved | 5
Simulation | Fictional, no production tests

## Evidence Register
record_id | control_id | control_domain | system | owner | due_date | evidence_date | status | evidence_uri | reviewer
CT-001 | ITGC-AC-01 | Access Governance | Microsoft Entra ID | IAM Lead | 2026-10-15 | 2026-10-14 | Approved | SIM://evidence/access-review-01 | Reviewer A
CT-002 | ITGC-AC-02 | Access Governance | Active Directory | IAM Lead | 2026-10-20 |  | Missing
CT-003 | ITGC-CH-01 | Change Control | Jira | Change Lead | 2026-10-25 | 2026-10-24 | Approved | SIM://evidence/change-ticket-03 | Reviewer B
CT-004 | ITGC-CH-02 | Change Control | Windows Server | Change Lead | 2026-10-22 | 2026-10-23 | Submitted | SIM://evidence/change-ticket-04
CT-005 | ITGC-VM-01 | Vulnerability Management | Rapid7-style feed | Security Lead | 2026-10-10 | 2026-10-09 | Rejected | SIM://evidence/vuln-report-05 | Reviewer C
CT-006 | ITGC-VM-02 | Vulnerability Management | Linux Server | Security Lead | 2026-11-05 | 2026-10-28 | Approved | SIM://evidence/vuln-report-06 | Reviewer C
CT-007 | ITGC-BA-01 | Backup and Restore | Storage Platform | Infrastructure Lead | 2026-10-27 | 2026-10-27 | Approved | SIM://evidence/restore-test-07 | Reviewer D
CT-008 | ITGC-BA-02 | Backup and Restore | Storage Platform | Infrastructure Lead | 2026-10-28 |  | Submitted |  | Reviewer D
CT-009 | ITGC-IR-01 | Incident Management | SIEM | Security Lead | 2026-11-02 | 2026-10-28 | Approved | SIM://evidence/incident-drill-09 | Reviewer C
CT-010 | ITGC-IR-02 | Incident Management | Service Desk | Operations Lead | 2026-10-19 | 2026-10-20 | Submitted | SIM://evidence/incident-record-10 | Reviewer B
CT-011 | ITGC-AC-03 | Access Governance | Microsoft 365 | IAM Lead | 2026-10-28 | 2026-10-28 | Approved | SIM://evidence/mfa-review-11 | Reviewer A
CT-012 | ITGC-CH-03 | Change Control | GitHub | Change Lead | 2026-11-03 | 2026-11-02 | Approved | SIM://evidence/change-pr-12 | Reviewer B

## Automated Results
record_id | control_id | control_domain | system | owner | due_date | evidence_date | status | evidence_uri | reviewer | evaluation | flags | days_overdue
CT-001 | ITGC-AC-01 | Access Governance | Microsoft Entra ID | IAM Lead | 2026-10-15 | 2026-10-14 | Approved | SIM://evidence/access-review-01 | Reviewer A | Ready for sample review |  | 0
CT-002 | ITGC-AC-02 | Access Governance | Active Directory | IAM Lead | 2026-10-20 |  | Missing |  |  | Needs review | Not approved; No evidence reference; No reviewer; Overdue | 9
CT-003 | ITGC-CH-01 | Change Control | Jira | Change Lead | 2026-10-25 | 2026-10-24 | Approved | SIM://evidence/change-ticket-03 | Reviewer B | Ready for sample review |  | 0
CT-004 | ITGC-CH-02 | Change Control | Windows Server | Change Lead | 2026-10-22 | 2026-10-23 | Submitted | SIM://evidence/change-ticket-04 |  | Needs review | Not approved; No reviewer; Overdue; Evidence after due date | 7
CT-005 | ITGC-VM-01 | Vulnerability Management | Rapid7-style feed | Security Lead | 2026-10-10 | 2026-10-09 | Rejected | SIM://evidence/vuln-report-05 | Reviewer C | Needs review | Not approved; Overdue | 19
CT-006 | ITGC-VM-02 | Vulnerability Management | Linux Server | Security Lead | 2026-11-05 | 2026-10-28 | Approved | SIM://evidence/vuln-report-06 | Reviewer C | Ready for sample review |  | 0
CT-007 | ITGC-BA-01 | Backup and Restore | Storage Platform | Infrastructure Lead | 2026-10-27 | 2026-10-27 | Approved | SIM://evidence/restore-test-07 | Reviewer D | Ready for sample review |  | 0
CT-008 | ITGC-BA-02 | Backup and Restore | Storage Platform | Infrastructure Lead | 2026-10-28 |  | Submitted |  | Reviewer D | Needs review | Not approved; No evidence reference; Overdue | 1
CT-009 | ITGC-IR-01 | Incident Management | SIEM | Security Lead | 2026-11-02 | 2026-10-28 | Approved | SIM://evidence/incident-drill-09 | Reviewer C | Ready for sample review |  | 0
CT-010 | ITGC-IR-02 | Incident Management | Service Desk | Operations Lead | 2026-10-19 | 2026-10-20 | Submitted | SIM://evidence/incident-record-10 | Reviewer B | Needs review | Not approved; Overdue; Evidence after due date | 10
CT-011 | ITGC-AC-03 | Access Governance | Microsoft 365 | IAM Lead | 2026-10-28 | 2026-10-28 | Approved | SIM://evidence/mfa-review-11 | Reviewer A | Ready for sample review |  | 0
CT-012 | ITGC-CH-03 | Change Control | GitHub | Change Lead | 2026-11-03 | 2026-11-02 | Approved | SIM://evidence/change-pr-12 | Reviewer B | Needs review | Evidence dated in future | 0